## Template
2020/2021
| BOARD & TEAM | NATIONAL NETWORK & TRAINING | INTERNATIONAL NETWORK & TRAINING | STEP PROMOTION | JOB HUNTING | STUDENT HUNTING | TRAINEE ENGAGEMENT | STEP RESEARCH PROJECT
JULY
AUGUST
SEPTEMBER |  |  | KAM Pilsen (2.-9.9.2020)
OCTOBER |  |  |  |  | JH deadline (TBC)
NOVEMBER |  |  | ICM Antalya (8.-15.11.2020) |  |  | External and Internal SH deadline(s) (TBC)
DECEMBER
JANUARY
FEBRUARY
MARCH |  |  | ICM (TBC) |  | JH deadline (TBC)
APRIL | [5 empty] | External and Internal SH deadline(s) (TBC)
MAY
JUNE
JULY

## EI Successor Example Draft
2020/2021
| BOARD & TEAM | INTERNATIONAL NETWORK & TRAINING | STEP PROMOTION | TRAINEESHIP PROVIDERS | STUDENT HUNTING | TRAINEE ENGAGEMENT | STEP RESEARCH PROJECT
JULY | Transition as a board |  | Prepare Joint JH - ELSA Alumni Promotion |  |  | Analyse the past evaluation forms | Compile the final report, share with Caselex
AUGUST | Opening the call for ELSA International STEP Team. JH Discussion with Board to Share Contacts. Job Hunting Media Card Update | Send an introduction email and set up a Facebook group. Pre-KAM calls and post-KAM updates Open Call | Finalise Joint JH - ELSA Alumni Promotion | EI TNPs + Partner Organisations & Alumni Network Introduction Email + STEP Calendar | Discuss with Ilke Webinar Approach Discuss with Maja, Professional Development Projects Discuss with Board STEP Week Plan | Send an introduction email, evaluation + certificates | Get feedback from Caselex
SEPTEMBER | Appointing and organising the ELSA International STEP Team ICM Prep | KAM Pilsen (2.-9.9.2020). Webinar - TNPs/Trainees Open Call | JH Promotion - ELSA Alumni/LinkedIn | SET Strategy & Training | Finalise Plans with S&C, Board and AA | Evaluation + certificates | Communicate the year's schedule and aims
OCTOBER | ICM Prep | Pre-ICM calls JH Officers Training through Training Platform Open Call | JH Promotion - ELSA Alumni/LinkedIn. STEP Launch MKT Kit/Posters/Material One Month Left Teaser Post | Hunt | Webinar Series - Professional Development Projects | Evaluation + certificates
NOVEMBER | Post-ICM "holiday" as a board ICM Prep | ICM Antalya (8.-15.11.2020); post-ICM updates Open Call | STEP Countdown; STEP Launch (20.11.2020) | JH deadline (9.11.2020) | Webinar Series - Professional Development Projects 2-6 November STEP Week | Evaluation + certificates | National Reports
DECEMBER | EIT Weekend (Matching) | Open Call | Countdown to application deadline Teaser for Selection Results | Send the matched candidates | External SH deadline (11.12.2020); Internal SH deadline (15.12.2020) | Evaluation + certificates
JANUARY | JH Discussion with Board to Share Contacts. Evaluation Mid - OYOP Training ICM Prep | Open Call | Re-Evaluate JH Promotion Results Out Post | Get the selection results, put the offer-holders in touch with the TNPs | Evaluation | Evaluation + certificates
FEBRUARY | ICM Prep | Pre-ICM calls JH Officers Training through Training Platform Open Call | JH Promotion - ELSA Alumni/LinkedIn | Re-Evaluate STEP Strategy & Training | Webinar Series - Professional Development Projects | Evaluation + certificates
MARCH | ICM Prep | ICM (TBC). Webinar - TNPs/Trainees Open Call | JH Promotion - ELSA Alumni/LinkedIn. STEP Launch MKT Kit/Posters/Material One Month Left Teaser Post | Hunt | Webinar Series - Professional Development Projects | Evaluation + certificates | National Reports
APRIL |  |  | STEP Countdown; STEP Launch (23.4.2021) | JH deadline (9.4.2021) | STEP Week | Evaluation + certificates
MAY | Matching | Open Call | Countdown to application deadline Teaser for Selection Results | Send the matched candidates | External SH deadline (14.5.2021); Internal SH deadline (18.5.2021) | Evaluation + certificates
JUNE | Evaluation | Open Call | Results Out Post | Get the selection results, put the offer-holders in touch with the TNPs | Webinar - Application Tips - Rejections | Evaluation + certificates | Final Reports
JULY | Deadline: Annual Report |  |  | Evaluation Meetings |  | Evaluation + certificates

## EI Predecessor Example Draft
2019/2020
| BOARD & TEAM | STEP NETWORK & TRAINING | STEP PROMOTION | TRAINEESHIP PROVIDERS | STUDENT HUNTING | TRAINEE ENGAGEMENT | STEP RESEARCH PROJECT
JULY | Transition as a board | Create the STEP Calendar 2019/2020 | Analyse past promotion strategies | Study the databases | Study the databases | Analyse the past evaluation forms | Analyse the legal issues affecting STEP from past ICM minutes
AUGUST | Opening the call for ELSA International STEP Team | Send an introduction email and set up a Facebook group; update the handbooks and guides | Update the website and prepare the promotion strategy/schedule | Introduce yourself and arrange meetings | Update the website, the SAF and other materials | Send an introduction email, evaluation + certificates | Prepare the concept, academic framework and guidelines; Secure a SRP Partner
SEPTEMBER | Appointing and organising the ELSA International STEP Team | Pre-KAM calls; KAM Istanbul; post-KAM updates; STEP Newsletter | Update the JH Media Card | Hunt | Introduce the concept of External Applicants to the Network | Evaluation + certificates | Present the SRP concept to the Network at KAM
OCTOBER | Synergy | Pre-ICM calls; ICM Opatija; post-ICM updates; STEP Newsletter | Update the colour scheme of the website and materials | Hunt | Promote External Applicants option | Evaluation + certificates | Present a more developed SRP concept to the Network at ICM
NOVEMBER | Post-ICM "holiday" as a board | STEP Newsletter + open call | STEP Countdown (11-17.11.2019) and STEP Launch (18.11.2019) | JH deadline (8.11.2019) | Promote External Applicants option | Evaluation + certificates | Discussion and feedback with the SRP Partner
DECEMBER | ELSA International Team Weekend | STEP Newsletter + open call | Countdown to application deadline (9.12.2020) | Send the matched candidates (22.12.2020) | Verification and approval deadline (14.12.2020); Matching (15-22.12.2020) | Evaluation + certificates | Finalise the materials for the launch date
JANUARY | Mid-OYOP; GDPR training; preparation for the ICM | STEP Newsletter + open call | Selection results | Get the selection results (10.1.2020); Put the TNPs in touch with the Trainees | Communicate the selection results (13.1.2020) | Evaluation + certificates | Launch the SRP
FEBRUARY | IPM Munich; preparation for the ICM | STEP Newsletter + open call | STEP logo competition | Hunt | Earliest start date (3.2.2020) | Evaluation + certificates | Provide guidance and further information to the Network
MARCH | COVID-19 | ICM Malta (cancelled); STEP Newsletter + many calls | COVID-19 | COVID-19 | COVID-19 | Evaluation + certificates; COVID-19 | The first interim national reports deadline
APRIL | COVID-19; Synergy; grant application; online ICM preparation | JH coaching; STEP Newsletter + many calls | Update the promotion strategy and schedule due to COVID-19 | COVID-19 | COVID-19 | Evaluation + certificates; COVID-19 | Review the submissions and give feedback
MAY | COVID-19; grant application; preparation of the ELSA Open Forum; preparation of a project with ELSA Alumni; online ICM preparation | Webinar on SAF 2.0; STEP Newsletter | STEP Countdown (1-7.5.2020) and STEP Launch (8.5.2020); Countdown to application deadline (29.5.2020); International Career Insights webinar and LinkedIn webinar | JH deadline (1.5.2020) | Update the website, the SAF and other materials | Evaluation + certificates; COVID-19 | Review the submissions and give feedback
JUNE | COVID-19; grant application; preparation of the ELSA Open Forum; preparation of a project with ELSA Alumni; online ICM preparation; preparation of the transition month | Pre-ICM calls; Online ICM; STEP Newsletter + open call on digital reception; Transition Toolkit Working Group | Post-promotion; selection results | Send the matched candidates (10.6.2020); Get the selection results (26.6.2020); Put the TNPs in touch with the Trainees | Verification and approval deadline (4.6.2020); Matching (5-9.6.2020); Communicate the selection results (29.6.2020) | Evaluation + certificates; COVID-19 | The second national reports deadline; prepare the materials for the STEP Trainees
JULY | Transition to the new board | STEP Newsletter | Applications tip webinar | Introduce your successor and arrange evaluation meetings | Earliest start date (20.7.2020) | Evaluation + certificates; COVID-19 | Appoint STEP Trainees for the SRP and compile the final report for the first year